## Risk and Gap Register
Risk ID | Category | Risk / Gap | Evidence | Potential Impact | Likelihood | Severity | Recommended Action | Owner | Status
R-01 | Product Readiness | Published flags may be mistaken for launch approval | Course rows include is_published; signed QA/release evidence not verified. | Incomplete product may launch. | Medium | High | Require launch checklist, QA evidence, defect closure and sign-off. | Product and Engineering | Open
R-02 | Commercial | Purchase records may be reported as revenue | 5 purchase rows; no amount or payment status in source. | Revenue overstatement and poor decisions. | High | Critical | Reconcile gateway/order amount, status, fees, refunds and entitlement. | Finance and Engineering | Open
R-03 | Commercial | Price field semantics unclear | price and discount_price fields exist; meanings need backend confirmation. | Incorrect price reporting or customer display. | Medium | High | Confirm definitions and approved price policy. | Product and Finance | Open
R-04 | Financial | Operating cost and margin unavailable | No verified cost ledger or approved budget. | Cannot assess unit economics or break-even. | High | High | Create approved cost ledger and budget. | Finance and Operations | Open
R-05 | User Operations | Sample size is too small for launch forecast | 3 student accounts in sample source. | Unreliable market/conversion assumptions. | High | Medium | Establish production cohort baseline; do not extrapolate sample. | Growth / Product Analytics | Open
R-06 | User Operations | Demo and live-class funnel not measurable | No verified demo/live attendance records in reviewed sample. | Cannot assess conversion or delivery participation. | High | High | Instrument demo booking/attendance and live session attendance. | Product and Learning Operations | Open
R-07 | Learning Operations | Learning activity sample is sparse | 4 progress rows and 1 streak row. | Engagement results may mislead. | High | Medium | Validate event completeness and course-level completion rules. | Learning Operations | Open
R-08 | Support | Support volume and SLA not measurable | No verified ticket, response or resolution records. | Unmanaged support workload and escalation. | High | High | Implement ticketing with severity, owner and timestamps. | Support and Operations | Open
R-09 | Technology | Availability, backup and rollback evidence absent | No uptime/incident/restore evidence in reviewed source set. | Outage and data-loss exposure. | Medium | High | Provide monitoring and tested backup restore/rollback. | Engineering / DevOps | Open
R-10 | Data Quality | Purchase-before-registration date anomaly | Purchase row 1 for user 3 is dated 1 January 2026; registration is dated 3 January 2026. | Lifecycle sequence may be inaccurate. | Medium | High | Check timezone, source clock and import history; preserve raw values. | Data / Backend | Open
R-11 | Product / Commercial | Payment-to-access workflow unverified | Purchase source has no gateway result or access-granted timestamp. | Payment may not map to correct access. | Medium | Critical | Test success, failure, duplicate callbacks, refunds and entitlement. | Engineering and Finance | Open
R-12 | Measurement | Targets and escalation thresholds need approval | Definitions exist but reliable baseline/approved targets not established. | Arbitrary or impractical targets. | Medium | High | Approve owner, cadence, threshold, denominator and escalation. | Management | Open
R-13 | Learning Outcomes | Assessment/certificate outcomes unsupported | Previously reviewed assessment template had empty assessment, question and response sheets. | Cannot evaluate assessment quality or certification outcomes. | Medium | Medium | Connect populated assessment, grading and certificate data. | Academic and Engineering | Open